## Agile Sprint Tracker
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 29-Dec-25 | 11-Jan-26 | Mahesh | Analyzing enterprise email workflow; Defining business-specific email categories; Reviewing ML approaches for text classification | Starting development without clear class definitions; Random experimentation without metric tracking | Consistent coding practice; Maintaining structured documentation | Finalized email categories and project roadmap; Prepared cleaned baseline dataset for modeling
2 | S2 | 12-Jan-26 | 25-Jan-26 | Mahesh | Building scalable preprocessing pipeline; Implementing normalization, tokenization, and stopword filtering; Generating TF-IDF feature matrix | Manual data cleaning outside pipeline; Rewriting preprocessing logic repeatedly | Frequent Git updates; Evaluating preprocessing impact on model performance | Developed reusable preprocessing module; Improved feature consistency across training and testing data
3 | S3 | 26-Jan-26 | 8-Feb-26 | Mahesh | Training and benchmarking classification models; Performing stratified train-test split; Applying cross-validation | Relying solely on accuracy for evaluation; Ignoring class-wise performance metrics | Monitoring precision, recall, and F1-score; Recording experiment results systematically | Identified Linear SVM as best-performing model; Documented comparative performance analysis
4 | S4 | 9-Feb-26 | 23-Feb-26 | Mahesh | Fine-tuning selected model; Integrating model into simple deployment interface; Conducting end-to-end testing | Postponing validation of edge-case emails; Skipping integration checks | Performance tracking; Code refactoring for maintainability | Completed working prototype; Validated model robustness; Prepared final internship documentation